{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Kế Hoạch"],"not_rendered":{"charts":1,"images":0,"macros":0,"external_links":1,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Kế Hoạch","index":0,"n_rows":50,"n_cols":12,"rows_kept":50,"cut":false,"hidden":false,"merged":[[36,1,36,2],[37,1,37,2],[29,1,29,2],[30,1,30,2],[31,1,31,2],[32,1,32,2],[33,1,33,2],[34,1,34,2],[24,1,24,2],[25,1,25,2],[26,1,26,2],[27,1,27,2],[28,1,28,2],[35,1,35,2],[18,1,18,2],[19,1,19,2],[20,1,20,2],[21,1,21,2],[22,1,22,2],[23,1,23,2],[12,1,12,2],[13,1,13,2],[14,1,14,2],[15,1,15,2],[16,1,16,2],[17,1,17,2],[8,1,8,2],[9,1,9,2],[10,1,10,2],[0,0,0,13],[1,5,3,5],[5,1,5,2],[6,1,6,2],[38,1,38,2],[39,1,39,2],[40,1,40,2],[41,1,41,2],[42,1,42,2],[43,1,43,2],[44,1,44,2],[45,1,45,2],[46,1,46,2],[47,1,47,2],[48,1,48,2],[49,1,49,2]],"flags":["formulas_cached_only"]}
["Nhật ký kiểm sát điện tử đối với vụ án Đinh Iô - Điều 173"]
[null,null,null,"Ngày bắt đầu","2021-01-01",null,"Việc Đang Làm",1,"Việc quá hạn"]
[null,null,null,"Ngày kết thúc","2021-12-12",null,"Việc Chưa Làm",1,1]
[null,null,null,"Hôm nay","2021-11-02",null,"Việc Hoàn Thành",1]
["Stt","Nội dung công việc",null,"Bắt đầu","Kết thúc","Người thực hiện","Trạng thái","Thực tế bắt đầu","Thực tế kết thúc","Cảnh báo số ngày còn lại","Khó khăn","Tình Trạng"]
[1,"Yêu cầu CQĐT thu thập làm rõ lý lịch bị can",null,"2021-10-26","2021-10-27","Đ/c Quyết","Hoàn Thành",null,"2021-10-27",""]
[2,"Yêu cầu CQĐT tiến hành trưng cầu giám định",null,"2021-10-27","2021-10-28","Đ/c Lai cán bộ điều tra","Quá Hạn",null,null,"số ngày quá hạn: 5 ngày"]
[3,"Tham gia hỏi cùng cùng ĐTV",null,"2021-11-02","2021-11-03","Đ/c Quyết","Đang Làm",null,null,"số ngày còn lại: 1 ngày"]
[4,"Tham gia thực nghiệm điều tra",null,"2021-11-03","2021-11-04","Đ/c Quyết","Chưa bắt đầu",null,null,"số ngày còn lại: 2 ngày"]
[5,{"$nulls":5},"",null,null,""]
[6,{"$nulls":5},"",null,null,""]
[7,{"$nulls":5},"",null,null,""]
[8,{"$nulls":5},"",null,null,""]
[9,{"$nulls":5},"",null,null,""]
[10,{"$nulls":5},"",null,null,""]
[11,{"$nulls":5},"",null,null,""]
[12,{"$nulls":5},"",null,null,""]
[13,{"$nulls":5},"",null,null,""]
[14,{"$nulls":5},"",null,null,""]
[15,{"$nulls":5},"",null,null,""]
[16,{"$nulls":5},"",null,null,""]
[17,{"$nulls":5},"",null,null,""]
[18,{"$nulls":5},"",null,null,""]
[19,{"$nulls":5},"",null,null,""]
[20,{"$nulls":5},"",null,null,""]
[21,{"$nulls":5},"",null,null,""]
[22,{"$nulls":5},"",null,null,""]
[23,{"$nulls":5},"",null,null,""]
[24,{"$nulls":5},"",null,null,""]
[25,{"$nulls":5},"",null,null,""]
[26,{"$nulls":5},"",null,null,""]
[27,{"$nulls":5},"",null,null,""]
[28,{"$nulls":5},"",null,null,""]
[29,{"$nulls":5},"",null,null,""]
[30,{"$nulls":5},"",null,null,""]
[31,{"$nulls":5},"",null,null,""]
[32,{"$nulls":5},"",null,null,""]
[33,{"$nulls":5},"",null,null,""]
[34,{"$nulls":5},"",null,null,""]
[35,{"$nulls":5},"",null,null,""]
[36,{"$nulls":5},"",null,null,""]
[37,{"$nulls":5},"",null,null,""]
[38,{"$nulls":5},"",null,null,""]
[39,{"$nulls":5},"",null,null,""]
[40,{"$nulls":5},"",null,null,""]
[41,{"$nulls":5},"",null,null,""]
[42,{"$nulls":5},"",null,null,""]
[43,{"$nulls":5},"",null,null,""]
[44,{"$nulls":5},"",null,null,""]
[45,{"$nulls":5},"",null,null,""]